{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["Sheet2","Sheet3"],"read":"whole","date_system":"1900"}

{"sheet":"Sheet2","index":0,"n_rows":11,"n_cols":3,"rows_kept":11,"merged":[[0,0,0,2],[2,0,2,2],[8,0,8,2],[10,0,10,2]]}
["消缺范围\n"]
["序号","存在问题","预估需要人工机械"]
["一、集电线路"]
[1,"部分箱变柜门外壳存在局部变形","小工工日：5个\n"]
[2,"32台风机及箱变高低压侧部分电缆防火封堵、内部电缆及光缆整理，卫生清洁","小工工日：94个\n高空工日：32个\n辅材：\n\n"]
[3,"部分电缆标示桩未设置明显的标志或标桩。","小工工日：2个\n电缆标示桩：21个"]
[4,"32台箱变到终端塔电缆沟需要复垦，种植，部分电缆标识桩破坏需重新安装","小工工日：152个\n小型运输车：12台班\n小挖机:12台班"]
[5,"线路消缺","高空工日：181个\n辅材：\n"]
["二、风机散水"]
[1,"风机散水沉降、有裂缝、散水边沿高于基础承台、伸缩缝未按要求进行施工，未灌密实，部分机位伸缩缝两侧污染严重，需清理等缺陷。需要消缺整改满足华电达标生产要求","小工工日：64\n\n辅材："]
["备注：1.以上暂估消缺项数量及类型不限于清单，具体根据现场实际情况据实结算；\n2.一般纳税人劳务税率按6%计（小规模3%计）；机械含司机及油料，税率按9%计；辅材按13%计，但最终税率按国家税务相关规定执行。\n3.所有劳务人员应签订劳务用工合同，购买保险并明确保险保险内容及金额，若发现人员有工作不胜任或不服从管理的，应及时终止其用工合同并清出现场，劳务人员报价应考虑食宿及交通费。"]

{"sheet":"Sheet3","index":1,"n_rows":15,"n_cols":8,"rows_kept":15,"merged":[[0,1,0,7],[1,2,1,3],[2,2,2,3],[3,2,3,3],[4,2,4,3],[5,2,5,3],[6,2,6,3],[7,1,13,1],[7,2,13,2],[14,1,14,7]]}
[null,"风电项目剩余消缺项\n(用工及材料清单)"]
[null,"序号","名称",null,"预估数量","单价","合计","备注"]
[null,1,"小工",null,285,null,null,"工日"]
[null,2,"大工",null,32]
[null,3,"高空",null,213,null,null,"工日"]
[null,4,"挖机",null,12,null,null,"台班"]
[null,5,"运输车",null,12,null,null,"台班"]
[null,6,"辅材","防火泥（块）",32,null,null,"（2kg/块）"]
[{"$nulls":3},"防火封板（张）",8,null,null,"1m*2m"]
[{"$nulls":3},"电缆标识桩（个）",205]
[{"$nulls":3},"绝缘胶带（黄绿红各10）",30,null,null,"35KV"]
[{"$nulls":3},"螺丝、开口销、防盗螺丝",3,null,null,"（各一包，具体按现场需求采购）"]
[{"$nulls":3},"硅酮耐候结构胶",128,null,null,"590ml"]
[{"$nulls":3},"草籽",2,null,null,"每袋50kg"]
[null,"备注：1.以上暂估消缺项数量及类型不限于清单，具体根据现场实际情况据实结算；\n2.一般纳税人劳务税率按6%计（小规模3%计）；机械含司机及油料，税率按9%计；辅材按13%计，但最终税率按国家税务相关规定执行。\n3.所有劳务人员应签订劳务用工合同，购买保险并明确保险保险内容及金额，若发现人员有工作不胜任或不服从管理的，应及时终止其用工合同并清出现场，劳务人员报价应考虑食宿及交通费。"]